## Sheet1
| Elif Merve | Emre Deniz | Fahri | Melike | Yunus
Week-1 (11 October - 18 October) | Cat Feeding System Solution Research | Valet System Solution Research | Where am I? Solution Research on Mapping | Where am I? Solution Research on Localization | Gimme Fast Project Solution Research
Brainstorming on all projects. Deciding what project we will be working on using the weighted table of all the projects.
Week-2 (19 October - 25 October) | Defining the Problem Statement and Societal Impact of the Project.
Brainstorming on the Project. Discussions on the Project Requirements and Objectives
| Outline of the Requirements for the Standards of the Product Will Be Decided |  |  | Deliverables and Expected Outcomes of the Project Will Be Decided
Week-3 (26 October - 1 November) | Brainstorming on the Project. Approach to the Solution of the Project
| Time Plan Will Be Prepared |  | Cost - Budget Analyzes Will Be Done